## Slide 1
THE DENT · BANGKOK
SEO & GEO AGENCY REPORT
thedent.co.th
Remediation Report &
90-Day Action Plan
Restoring crawlability and building durable SEO + AI-search visibility.
Prepared by · SEO & GEO Agency (Agent Orchestra)
Date · 2026-04-19
Status · Action required — site currently uncrawlable

## Slide 2
01 · EXECUTIVE SUMMARY
The site is currently invisible to search and AI engines.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
1 / 16
HTTP STATUS RETURNED TO CRAWLERS
403
host_not_allowed
Homepage, www, robots.txt, sitemap.xml, and llms.txt all blocked at the edge.
WHAT THIS MEANS
• Google cannot crawl or refresh the site — ranked pages will drop out of the index.
• ChatGPT, Perplexity, Google AI Overviews, Gemini, and Claude cannot read the site at query time — the clinic is excluded from AI answers.
• Every other on-page or content issue is invisible behind this block and cannot be diagnosed until crawlers can reach the site.
MOST URGENT ACTION (TODAY)
Remove the host_not_allowed edge rule and verify
curl -I https://thedent.co.th/ returns HTTP 200 for both a browser and a Googlebot user agent.

## Slide 3
02 · APPROACH
A two-stage program: unblock, then build.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
2 / 16
STAGE 1 · EMERGENCY
Restore crawlability (Days 0–7)
• Remove edge block; site returns 200 to all crawlers
• Publish working robots.txt, sitemap.xml, and llms.txt
• Resubmit to Google Search Console and Bing
• Allowlist major AI-engine crawlers explicitly
• Capture a baseline crawl + AI-citation snapshot once reachable
STAGE 2 · BUILD-OUT
Foundations to citations (Weeks 2–13)
• Phase 1 — technical SEO, schema, local + Core Web Vitals
• Phase 2 — E-E-A-T (doctor profiles, reviewer signals) + content
• Phase 3 — entity footprint, GEO scale, durable measurement
• Outcome — indexed, optimized, and reliably cited by AI engines
Every Phase 1–3 task assumes Stage 1 is complete. Without crawlability, the rest is unmeasurable.

## Slide 4
03 · CURRENT STATE
Crawlability — every key URL is denied at the edge.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
3 / 16
Resource
Status
Impact
https://thedent.co.th/
403 host_not_allowed
Homepage uncrawlable
https://www.thedent.co.th/
403 host_not_allowed
www variant uncrawlable
https://thedent.co.th/robots.txt
403
Google treats as "unreachable" — crawl slows / stops if >30 days
https://thedent.co.th/sitemap.xml
403
No URL discovery aid
https://thedent.co.th/llms.txt
403
No AI-engine site map — likely doesn't exist yet
DIAGNOSIS
An origin / edge host-allowlist (CDN host rule, reverse-proxy server_name, or origin firewall) rejects general traffic before
any application logic runs. The block is indiscriminate, not bot-specific. TLS/HTTP2 and DNS are healthy — recovery is near-instant once the rule is corrected.

## Slide 5
04 · IMPACT
Left unfixed, citation visibility decays to zero.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
4 / 16
SEO IMPACT
Indexation + measurement blocked
• Persistent 403s → deindexing of ranked pages
• New / updated pages will not be discovered
• PageSpeed, Lighthouse, and crawler audits cannot run against a 403
• Silent duration unknown — third-party allowlisted monitors may have missed it
GEO · CITATION-EXTINCTION TIMELINE
T + 0–4 weeks
Cached snapshots in Bing/Google/Common Crawl still surface; existing training data still references the site.
T + 1–3 months
Caches expire. Engines that re-verify before citing (Perplexity, ChatGPT browsing) silently drop the clinic.
T + 6 months+
Next-gen training corpora (fresh GPTBot/CCBot crawls) lack the site entirely. Open-crawl competitors take the citation slots.

## Slide 6
05 · CURRENT STATE
Foundations that are already healthy.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
5 / 16
HTTPS / HTTP-2
Configured and negotiating cleanly. No protocol-level concerns.
DNS
Resolves to a single clean A record (210.246.201.242). No split-horizon issues.
Structured deny
Fast, headered (x-deny-reason). Easy to diagnose, near-instant to undo.
Implication
Stage 1 recovery should be measured in hours, not weeks. The hard work is everything that comes after —
rebuilding indexation, schema, local presence, E-E-A-T signals, and the entity footprint that drives AI citations.

## Slide 7
06 · PLAN OVERVIEW
The 90-day plan at a glance.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
6 / 16
Wkickoff
W2
W4
W6
W8
W10
W12
P0 Emergency
P1 Technical
P2 E-E-A-T
P3 Entity & GEO
PHASE 0 · Days 0–7
Emergency unblock
Site returns 200 to crawlers. Baseline measurement becomes possible.
PHASE 1 · Weeks 2–5
Technical & local
Clean, indexable, schema-rich, locally-optimized site — once crawlers can read it.
PHASE 2 · Weeks 5–9
E-E-A-T & content
Medical-grade trust signals plus the first wave of citation-shaped pillars.
PHASE 3 · Weeks 9–13
Entity & GEO scale
LLMs reliably recognize and cite the clinic. Durable monthly measurement loop.

## Slide 8
07–10 · PHASE 0 DETAIL
PHASE 0 — Emergency unblock
thedent.co.th · SEO & GEO Remediation · 2026-04-19
7 / 16
Days 0–7 · GOAL: Site returns 200 to all crawlers; baseline measurement becomes possible.
#
Action
Owner
Effort
0.1
Locate and remove the host_not_allowed edge / WAF / origin rule
DevOps
S ≤1d
0.2
Ensure robots.txt returns 200 (serve as static, outside gated path)
DevOps
S ≤1d
0.3
Ensure sitemap.xml returns 200 and is current
DevOps
S ≤1d
0.4
Publish AI-bot-friendly robots.txt (allow major answer engines)
DevOps + GEO
S ≤1d
0.5
Publish initial llms.txt at root
GEO
S ≤1d
0.6
GSC: URL Inspection live test; resubmit sitemap; request indexing of top 10 URLs
SEO
S ≤1d
0.7
Bing Webmaster Tools: submit sitemap (powers Copilot / ChatGPT retrieval)
SEO
S ≤1d
0.8
Add a synthetic Googlebot-UA probe to monitoring (external IP)
DevOps
S ≤1d
0.9
Baseline: full crawl audit + tracked-query battery across ChatGPT/Perplexity/AIO/Gemini/Claude
SEO + GEO
M 2–5d
EXIT CRITERIA
All key URLs return 200; sitemap + robots + llms.txt live; GSC fetching successfully; baseline audits captured.

## Slide 9
07–10 · PHASE 1 DETAIL
PHASE 1 — Technical & local foundations
thedent.co.th · SEO & GEO Remediation · 2026-04-19
8 / 16
Weeks 2–5 · GOAL: Clean, indexable, schema-rich, locally-optimized site.
#
Action
Owner
Effort
1.1
Full on-page audit: titles, meta, H-structure, canonicals, hreflang TH↔EN, alt text
SEO
M 2–5d
1.2
Fix canonical + hreflang pairing across all TH/EN equivalents
SEO + Dev
M 2–5d
1.3
Core Web Vitals pass: LCP <2.5s, INP <200ms, CLS <0.1 on mobile
Dev
L 1–3w
1.4
Site-wide schema: MedicalClinic/Dentist, Organization + sameAs, BreadcrumbList
SEO + Dev
M 2–5d
1.5
Per-service-page MedicalProcedure schema (howPerformed, preparation, followup)
SEO + Dev
M 2–5d
1.6
Google Business Profile per branch + NAP consistency audit
SEO
M 2–5d
1.7
Local citations cleanup across Thai + medical-tourism directories
SEO
M 2–5d
1.8
Internal-link graph: eliminate orphan service pages; pillar↔supporting
SEO + Content
M 2–5d
1.9
Fix any noindex / X-Robots-Tag leakage; confirm clean response headers
Dev
S ≤1d
EXIT CRITERIA
Zero P0/P1 technical issues open; schema validates; CWV "Good"; GBP complete per branch; no orphan service pages.

## Slide 10
07–10 · PHASE 2 DETAIL
PHASE 2 — E-E-A-T & content engine
thedent.co.th · SEO & GEO Remediation · 2026-04-19
9 / 16
Weeks 5–9 · GOAL: Medical-grade trust signals + first wave of citation-shaped content.
#
Action
Owner
Effort
2.1
Doctor profile pages with Person schema (credentials, worksFor, sameAs)
Content + SEO
M 2–5d
2.2
Add reviewer byline + reviewedBy + visible lastReviewed date to all YMYL pages
Content
M 2–5d
2.3
Confirm clinic facts (services, prices, brands stocked, branches) — unblocks content
Client
S ≤1d
2.4
Publish priority-cluster pillar + supporting content via brief→draft→review→revise
Planner→Creator→SEO+GEO
L 1–3w
2.5
Convert top revenue pages to citation shape (answer-first, Q-H2s, tables, FAQ)
Creator + GEO
L 1–3w
2.6
Wire FAQPage schema to every Q&A block
SEO + Dev
M 2–5d
2.7
Begin Thai-language adaptations (native-speaker reviewed) of best EN pieces
Creator
M 2–5d
EXIT CRITERIA
Doctor profiles live; YMYL pages carry reviewer signals; one citation-optimized pillar live per top cluster; sample implant-cost guide finalized.

## Slide 11
07–10 · PHASE 3 DETAIL
PHASE 3 — Entity footprint, GEO scale & measurement
thedent.co.th · SEO & GEO Remediation · 2026-04-19
10 / 16
Weeks 9–13 · GOAL: LLMs reliably recognize and cite the clinic; durable measurement loop established.
#
Action
Owner
Effort
3.1
File Wikidata entry (Organization + sameAs to GBP, LinkedIn, FB, IG)
GEO
M 2–5d
3.2
Consistent entity profile across DentaVox, WhatClinic, Dental Departures, Bookimed
GEO + Marketing
M 2–5d
3.3
Publish llms-full.txt with condensed high-value content
GEO
M 2–5d
3.4
Original-data asset (e.g. anonymized 2025 price ranges / brand mix)
GEO + Client
M 2–5d
3.5
Drive Perplexity / AIO discovery via social signals to key pages
Marketing
S ≤1d
3.6
Monthly tracked-query battery (top 20 questions, TH+EN) → citation share
GEO
M 2–5d
3.7
Quarterly roadmap: convert audit deltas into next content calendar
Planner
M 2–5d
EXIT CRITERIA
Wikidata + directory entity consistency live; llms-full.txt published; first original-data asset live; monthly AI-citation tracking running with delta.

## Slide 12
11 · KPIS
What success looks like at Day 30, 60, 90.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
11 / 16
Metric
Baseline (today)
Day 30
Day 60
Day 90
Crawlable URLs (HTTP 200)
~0% (403)
100%
100%
100%
Pages indexed (GSC)
Unknown / decaying
Recovering
Back to pre-block + new
Growth trend
Service pages with valid schema
Unknown
Core types live
All service pages
All pages
Branches with complete GBP
TBD
Audited
Complete
Optimized + posting
YMYL pages with reviewer signals
~0
Template live
50%
100%
Citation-optimized pillars published
0 (1 draft)
1
3
5 (one per cluster)
AI-citation share (tracked queries)
~0 (unreachable)
Baseline set
First citations
Measurable share
Core Web Vitals (mobile)
Unmeasurable
Measured
Improving
All "Good"
Review cadence: weekly during Phase 0–1; bi-weekly during Phase 2–3. Monthly KPI report to client.

## Slide 13
12 · DEPENDENCIES & RISKS
What could slow us down — and how we mitigate it.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
12 / 16
Dependency / risk
Impact
Mitigation
DevOps access to CDN / WAF / origin config
Blocks everything
Escalate today; Phase 0 cannot start without it
Client confirmation of services / prices / brands / branches
Blocks content (P2)
Collect in week 1, in parallel with Phase 0
Search Console + GA4 access
Blocks measurement
Request access now
Thai native-speaker review capacity
Blocks TH publishing
Identify reviewer in week 1
Doctor credentials + photos for bylines
Blocks E-E-A-T
Collect during Phase 1
The 403 recurs after fix (config not durable)
Re-extinction
Synthetic Googlebot probe + static robots.txt

## Slide 14
13 · THIS WEEK
Five moves to start right now.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
13 / 16
1
DEVOPS
Remove the host_not_allowed edge rule; verify HTTP 200 for browser + Googlebot + GPTBot. (today)
2
DEVOPS + GEO
Publish corrected robots.txt, sitemap.xml, and llms.txt. (Day 0–1)
3
SEO
Resubmit sitemap and request reindexing in Google Search Console + Bing. (Day 1–2)
4
CLIENT
Start compiling confirmed services, prices, implant / aligner brands, branches, doctor credentials. (week 1)
5
SEO + GEO
Capture baseline crawl audit + AI tracked-query battery once the site is reachable. (Day 3–5)

## Slide 15
14 · ROLES
Who does what across the program.
thedent.co.th · SEO & GEO Remediation · 2026-04-19
14 / 16
Role
Primary responsibilities
Stage
Client
Approve facts (services, prices, brands, doctor credentials, branches); grant GSC/GA4 access; sign-off content.
All
DevOps
Remove edge block, manage robots/sitemap/llms.txt, fix CWV, deploy schema, run synthetic crawler probe.
P0–P1
SEO expert
Audits, on-page and local SEO, schema design, internal links, GBP optimization, KPI tracking.
All
GEO expert
Crawler-allowlist policy, llms.txt/llms-full.txt, entity footprint, citation-shape requirements, AI-citation monitoring.
All
Content planner
Cluster map, keyword registry, calendar, briefs, backlog prioritization.
P2–P3
Content creator
Drafts and revises copy in TH + EN; executes briefs from planner with SEO + GEO requirements.
P2–P3
Native-speaker reviewer
Reviews all Thai-language copy before publish.
P2–P3

## Slide 16
THE DENT · BANGKOK
AGENCY
SEO & GEO
Agent Orchestra
NEXT STEP
Clear the block.
Then we build.
Once thedent.co.th returns 200 to crawlers, the 90-day plan executes on schedule.
Deliverables already in workspace/
• plans/2026-04-19-remediation-report-90day-plan.md — the long-form report
• seo-audits/2026-04-19-thedent-live-audit.md — live SEO findings
• geo-audits/2026-04-19-thedent-live-audit.md — live GEO findings + ready-to-paste robots.txt + llms.txt
• content/en/dental-implants-cost-bangkok-2026.md — sample citation-shaped pillar
• plans/calendar-2026-W17.md — example weekly editorial calendar